PMO_Risk_Recurrence_Predictor_Workflow

The Problem

Current State

Pain Point Impact

Risk registers in scattered Excel files

Risks are identified reactively during meetings, not proactively beforehand.

No historical learning - Same risks repeat across projects because past data isn't leveraged.

SLA deadlines tracked in memory or calendars. Missed deadlines. Risks silently worsen. No accountability.

Manual owner notification- PMs must remember to email each owner individually.

No audit trail -Can't trace who changed what or when a risk was resolved.

Hours spent on weekly reports  PM manually counts risks across spreadsheets for leadership.

Target State

A PM creates a project → the system suggests risks from similar past projects with LLM analysis → PM walks into the kickoff   → captures new risks live → every owner gets notified after the kickoff and risk is assigned → the system monitors deadlines → escalates if ignored (becomes an issue)→ tracks resolution → feeds learnings back into the knowledge base.

The Solution — How It Works

The Flow in Detail

1. PM creates project

Types project name (free text)

Selects Project Type (dropdown: IT Infrastructure, Software Dev, etc.)

Selects Department (dropdown: Digital Advisory, Technology, etc.)

Selects PM, Start Date, Stage Gate

Clicks Create

2. SYSTEM RESPONDS

Queries Historical Risks WHERE ProjectType matches

Sends all matching risks to Azure OpenAI

LLM generates:

Risk landscape overview (with source citations)

Per-risk analysis (why it matters, is the plan sufficient)

Recommendations (pre-kickoff actions, root cause patterns)

Presents suggested risks to PM

3. PM REVIEWS SUGGESTIONS

Accepts risks → added to Active Register with SLA imputed by PM

Edits risks → modifies fields before accepting

Dismisses risks → logged, won't reappear

Every accepted risk: owner notified, SLA set, dashboard updated

4. DURING CLIENT KICKOFF

PM references prepared risks with client

Client raises NEW risks → PM uses Quick Add

Custom risks get same treatment: SLA, owner notification, monitoring

5. AFTER MEETING

PM runs LLM Re-scan on full register

LLM identifies new dependency chains

PM updates response plans, shares final register with client

6. ONGOING MONITORING

SLA check on all Accepted + In Progress risks

Before deadline (HIGH) / (MEDIUM): reminder email to owner

Deadline passed, no activity: auto-escalation

Status → Escalated (becomes issue)

Email to Owner + PM + PMO Lead

weekly summary email to PM + PMO Lead

7. RESOLUTION

Owner marks Resolved → system records resolution time

PM reviews → fills closure form (root cause, what worked, etc.)

Risk closed → read-only → feeds Historical Risks list

Next project's suggestions get smarter

The PM's Journey

Before the Kickoff

PM Sarah creates "NHIA Cloud Migration" project.

Project Type: IT Infrastructure

Department: Digital Advisory

The system responds:

24 risks suggested from 3 historical IT Infrastructure projects

LLM OVERVIEW:

"Based on 24 risks across 3 projects:

• 6 High, 15 Medium, 3 Low severity

• Top concern: Resource staffing — appeared in ALL 3 projects

• Recurring pattern: AWS account delays in 2 of 3 projects

• Recommendation: Prioritize account provisioning before Week 1"

Sarah reviews the suggestions. She accepts 8 risks relevant to NHIA.

She dismisses 16 that don't apply (different tech stack).

Each accepted risk gets an SLA deadline imputed by the PM. Each owner gets an email.

Sarah now has a prepared Risk Register.

She reads the LLM's per-risk analysis:

RSK-008 (Resource staffing): "This is the most dangerous risk.

High likelihood × High impact. Do NOT accept without written

resource commitments. [R8, NHIA-AWS-RR-1.0.xlsx ]"

During the Kickoff

Sarah walks NHIA through the project plan. She references the prepared risks:

"We've seen on similar projects that AWS account provisioning delays

can block all downstream workstreams. Our plan is to provision accounts

by Day 5. Does that align with your timeline?"

NHIA CTO: "Yes, and also  we have a legacy Oracle database that

nobody has documented. The DBA left 3 years ago."

Sarah opens the Quick Add form :

Description: "Legacy Oracle DB — undocumented, DBA departed"

Category: Technical | Likelihood: High | Impact: High

Owner: Solution Architect

Clicks Add

NHIA Compliance: "We need SOC 2 certification before go-live.

Our compliance team is backed up 6 months."

Sarah Quick Adds again:

Description: "SOC 2 compliance backlog 6-month queue"

Category: Compliance | Likelihood: High | Impact: High

Owner: PM

Clicks Add

Both new risks appear in the register immediately.

Both owners get notified. Both have 24-hour SLA deadlines.

Dashboard updates: 8 → 10 risks.

After the Kickoff

Back at her desk, Sarah opens the project dashboard.

She sees: 10 risks (8 historical + 2 custom).

She clicks "Run LLM Re-scan."

The LLM analyzes the full 10-risk register and responds:

UPDATED ANALYSIS

Two new HIGH risks added during kickoff.

RSK-009 (Legacy Oracle DB) — amplifies existing risks RSK-004 and RSK-007.

RSK-010 (SOC 2 backlog) — creates new dependency chain:

RSK-001 (AWS accounts) → RSK-010 (SOC 2) → Go-live BLOCKED

WARNING: If SOC 2 takes 6 months and AWS accounts are provisioned

on schedule, you'll have infrastructure ready with no compliance

sign-off. Start SOC 2 process THIS WEEK. Adjust go-live date if

certification can't be compressed.

Sarah updates the response plans. She adds detailed notes.

She shares the register with NHIA for confirmation.

Ongoing

Every hour, the system checks all open risks.

RSK-001 (AWS accounts): Cloud Team updates status to "In Progress"

on Day 2. SLA satisfied.

RSK-008 (Resource staffing): No update for 20 hours.

System sends reminder at 4-hour warning.

Sarah sees the reminder, follows up with the functional manager.

Status updated to "In Progress" at Hour 22. SLA satisfied.

RSK-003 (Responsibility boundaries): No update.

Hour 24 — SLA breached.

Status → Escalated.

Emails to Owner + Sarah + PMO Lead.

Sarah gets the weekly summary email.

"3 risks resolved this week. 1 escalated. 7 still open.

Avg resolution time: 2-3 days."

She checks the Power BI dashboard:

Resolution rate: 38%. SLA compliance: 75%.

Top risk category: Technical (3 risks, slowest to resolve).

5. What the System Does Automatically

Automatic System Actions

- Project Created: Query historical risks by Project Type, perform LLM analysis, and present suggested risks to the Project Manager.

- Project Manager Accepts a Risk: Create the risk in the Active Risk Register, assign an SLA deadline, and notify the Risk Owner, Project Manager, Head of PM, and Practice Lead.

- Risk Owner Clicks the Email Link: Open the authenticated SharePoint edit form without requiring a separate login.

- Risk Owner Updates the Risk: Detect activity, mark the SLA as satisfied, and stop further reminder notifications.

- Hourly Monitoring: Check all risks with a status of Accepted or In Progress. Send reminder notifications at the configured warning threshold (4 hours for High risks and 12 hours for Medium risks) and escalate risks that breach their SLA.

- SLA Breach: Automatically change the risk status to Escalated and send email notifications to the Risk Owner, Project Manager, and PMO Lead.

- Risk Owner Marks the Risk as Resolved: Record the resolution time, notify the Project Manager for review, and update the reporting dashboard.

- Project Manager Closes the Risk: Record the root cause and resolution category, add the risk to the Historical Risks repository, and make the record read-only.

- Every Monday at 8:00 AM: Generate and email a weekly summary showing risk counts by severity, the number of escalated risks, and the overall resolution rate to the Project Manager and PMO Lead.

- Project Manager Runs the LLM Re-scan: Send the complete risk register to Azure OpenAI to generate an updated risk analysis, including dependency chains and additional recommendations.

Historical Risks (Knowledge Base – Imported Once)

- Risk ID – Text field imported from the original Excel file.

- Project Type – Choice field used to match historical risks with new projects of the same type.

- Department – Choice field populated from the Excel metadata.

- Risk Description – Multiple lines of text containing the detailed description of the risk.

- Risk Category – Choice field imported from the Excel file.

- Subcategory – Text field providing additional classification of the risk.

- Likelihood – Choice field with values such as Low, Medium, or High.

- Impact – Choice field with values such as Low, Medium, or High.

- Risk Rating – Choice field indicating the overall risk level (Low, Medium, or High).

- Response Strategy – Choice field with values such as Mitigate, Transfer, Avoid, or Accept.

- Response Plan – Multiple lines of text describing the planned mitigation or response.

- Risk Owner – Text field identifying the person responsible for managing the risk.

- Source File Name – Text field containing the name of the original imported risk register (for example, NHIA-AWS-RR-1.0.xlsx).

- Source File URL – Hyperlink to the original risk register document for traceability and reference.

Active Risks (Current Projects – Populated by the System and Project Manager)

The list contains the following fields:

- Project – Lookup field that links the risk to a project in the Projects list.

- Active Risk ID – Automatically generated text field (for example, RSK-001, RSK-002).

- Risk Description – Multiple lines of text containing the risk description, either imported from historical suggestions or entered manually.

- Risk Category – Choice field populated from historical data or selected by the Project Manager.

- Subcategory – Text field providing additional classification.

- Likelihood – Choice field indicating the probability of the risk occurring.

- Impact – Choice field indicating the potential effect of the risk.

- Risk Rating – Choice field automatically calculated from the Likelihood and Impact values.

- Response Strategy – Choice field indicating the selected treatment approach (for example, Mitigate, Transfer, Avoid, or Accept).

- Response Plan – Multiple lines of text describing the planned mitigation activities.

- Risk Owner – Person field identifying the individual responsible for managing the risk.

- Practice Lead – Person field automatically populated based on the selected department or manually selected by the Project Manager.

- Status – Choice field representing the current stage of the risk lifecycle (Suggested, Accepted, In Progress, Escalated, Resolved, or Closed).

- Source – Choice field identifying where the risk originated (Historical, Custom, or Kickoff Meeting).

- Raised By – Text field identifying the individual who reported or identified the risk.

- Identified During – Choice field indicating when the risk was identified (Kickoff Meeting, Design Review, Weekly Stand-up, etc.).

- Source File Name – Text field storing the name of the original historical risk register for traceability.

- Source File URL – Hyperlink to the original source document.

- Source Risk ID – Text field containing the identifier of the original historical risk.

- LLM Analysis – Multiple lines of text storing the AI-generated risk analysis at the time the risk is accepted.

- SLA Deadline – Date and time field automatically calculated based on the assigned SLA.

- SLA Acknowledged – Yes/No field indicating whether the Risk Owner has acknowledged the assigned risk.

- Accepted Date – Date and time field automatically populated when the risk is accepted.

- Resolved Date – Date and time field automatically populated when the Risk Owner marks the risk as resolved.

- Closed Date – Date and time field automatically populated when the Project Manager closes the risk.

- Root Cause – Multiple lines of text completed by the Project Manager during the closure process.

- What Worked – Multiple lines of text documenting successful mitigation actions and lessons learned.

- Resolution Category – Choice field classifying the reason for the resolution (for example, Process Failure, Resource Gap, or Technical Issue).

Configuration Lists (One-Time Setup)

The solution also includes configuration lists that store system-wide settings, SLA thresholds, notification recipients, and department-to-practice lead mappings. These lists are maintained by administrators and referenced automatically by workflows and automation throughout the solution.

Settings:

| Title | Value |

Head of PM - jane.adeola@company.com |

PMO Lead -emeka.nwankwo@company.com |

SLA_Hours_HIGH -24 |

SLA_Hours_MEDIUM -48 |

SLA_Hours_LOW -120

SLA_Warning_HIGH - 4

SLA_Warning_MEDIUM- 12

Department Leads:

Department Practice Lead Email

| Cloud Infrastructure | Mike Eze | mike.eze@company.com |

| Solution Architecture | Amina Bello | amina.bello@company.com |

| Security | Tunde Okafor | tunde.okafor@company.com |

| Applications | Chioma Nwosu | chioma.nwosu@company.com |

| Project Management | Jane Adeola | jane.adeola@company.com |

8. SLA Monitoring & Activity Detection

SLA Deadlines

The SLA configuration is as follows:

- High Risk

  - SLA Deadline: 24 hours

  - Warning Notification: 4 hours before the deadline

- Medium Risk

  - SLA Deadline: 48 hours

  - Warning Notification: 12 hours before the deadline

- Low Risk

  - SLA Deadline: 5 days

  - Warning Notification: 24 hours before the deadline

What Counts as Activity

The system uses SharePoint's built-in tracking capabilities to determine whether a Risk Owner has taken action on an assigned risk. Any of the following actions are considered valid activity and permanently satisfy the Service Level Agreement (SLA):

- Status Changed – The risk status changes from Accepted to any other status, such as In Progress, Resolved, or Closed.

- Any Field Edited – The system detects that the SharePoint Modified timestamp is later than the Created timestamp, indicating that one or more fields have been updated.

- Risk Owner Clicks "Acknowledge" – The SLA Acknowledged field is set to Yes, confirming that the Risk Owner has acknowledged responsibility for the risk.

Once any of these actions is detected, the system marks the SLA as satisfied and stops sending reminder notifications for that risk.

The system doesn't care WHAT the owner did — just that they did SOMETHING before the clock ran out.

Hourly Check Logic

For every risk WHERE Status = "Accepted" OR "In Progress":

Check 1: Modified > Created?           → YES = Activity

Check 2: Status ≠ "Accepted"?          → YES = Activity

Check 3: SLAAcknowledged = Yes?         → YES = Activity

ALL NO → Check the clock:

Deadline passed?     → BREACH  (escalate + notify)

Within warning?      → WARNING  (remind owner)

Plenty of time?      → OK  (check again next hour)

Activity Detected → SLA Satisfied Permanently

Once the owner does ANYTHING, the SLA is permanently satisfied. Even if status goes back to "Accepted" later, the Modified timestamp already proves they responded. No more reminders for that risk.

9. Risk Resolution & Closure

Status Lifecycle

Accepted ──→ In Progress ──→ Resolved ──→ Closed ──→ Knowledge Base

Risk Resolution and Closure Process

The risk resolution process follows a structured lifecycle to ensure that every risk is properly tracked, reviewed, and captured as organizational knowledge.

- Owner Works on the Risk

  - The assigned Risk Owner implements the agreed response plan.

  - The SLA remains active until the owner takes an action that satisfies the SLA requirements.

- Owner Marks the Risk as Resolved

  - Once the mitigation activities have been completed, the Risk Owner marks the risk as Resolved.

  - The system records:

    - Resolution Date

    - Resolution Time

    - Name of the user who resolved the risk

  - The SLA is considered satisfied.

- Project Manager Reviews and Closes the Risk

  - The Project Manager verifies that the risk has been adequately addressed.

  - During closure, the Project Manager documents:

    - Root Cause

    - What Worked

    - Resolution Category

  - The system records the Closed Date and marks the risk as Read-Only to preserve the audit trail.

- Knowledge Base Update

  - After the risk is closed, the system adds the completed risk to the Historical Risks repository.

  - The recorded lessons learned, root cause, and resolution details become part of the organization's knowledge base.

  - These historical records are used to improve AI-generated risk suggestions and recommendations for future projects of a similar type.

What the PM Sees

Dashboard Status Breakdown:

2 Accepted        (awaiting first action)

3 In Progress     (owners working on them)

1 Escalated       (SLA breached)

2 Resolved         (awaiting PM closure review)

1 Closed           (formally done, read-only)

Resolution Metrics:

Resolution Rate: 38% (3 of 8)

Avg Resolution Time: 2.3 days

Escalated risks take 0.8 days longer to resolve

Closure → Knowledge Base

When PM closes a risk (fills root cause, what worked, resolution category), the system adds it to Historical Risks. The next project of the same type gets richer suggestions:

"Legacy Oracle DB risk [RSK-009, NHIA-AWS-RR-LIVE] — resolved by engaging Oracle consultant (3 weeks, $15K). Recommend database audit in all IT Infrastructure kickoffs."

10. Notifications & Escalation Chain

When a Risk Owner is Assigned

PM selects David Okonkwo as Risk Owner → clicks Save

System triggers:

TO: David Okonkwo (Risk Owner)

Subject: "NEW RISK — RSK-009 Legacy Oracle DB (HIGH, 24h SLA)"

Body: Risk details + response plan + SLA deadline

[Update Status] button → opens SharePoint edit form

[Add Notes] button → opens SharePoint edit form

CC: Sarah Okonkwo (Project Manager)

CC: Jane Adeola (Head of PM) — from Settings list

CC: Mike Eze (Practice Lead) — auto-looked up from Department Leads

Escalation Chain

SLA Breached:

Risk status → Escalated (auto)- Risk becomes an issue

Email to Risk Owner: "RSK-009 ESCALATED — SLA breached"

Email to PM: same details + "action required"

Email to PMO Lead: same details + escalation context

Dashboard: risk highlighted red, moves to Escalated section

PM/PMO Lead must acknowledge within a stipulated time.

If unacknowledged, reminder sent.

Only PM or PMO Lead can de-escalate (with rationale).

Dashboard & Analytics

Dashboard

Project Overview:

• KPI cards: Total Risks, High Count, Escalated Count, SLA Compliance %

• Donut chart: Risk distribution by rating

• Stacked bar: Risk count by status

• Horizontal bar: Risk count by owner

• Treemap: Risk count by category

• SLA timeline: Gantt-style countdown bars per risk

• Slicers: Project, Rating, Status, Owner

Risk Register Detail:

• Full table with conditional formatting (color by rating, highlight escalated)

• Search + multi-column filters

• Click any row → drills through to detail page

Risk Detail (Drill-Through):

• Full risk information (description, plan, LLM analysis)

• Status history timeline with timestamps

• Source file link

• Resolution metrics (if resolved)

Page 4 — Portfolio View (Multi-Project):

• Risk by project (stacked bar)

• Project × Category heatmap

• Escalation trend (line chart over weeks)

• Portfolio KPIs (total risks, SLA compliance across all projects)

Implementation Plan

Build Phases

Foundation

Task - Effort

Create SharePoint Lists: Projects, Active Risks, Historical Risks, Settings, Department Leads

Create Document Library: upload original risk register files

Import NHIA-AWS-RR-1.0.xlsx into Historical Risks list

Provision Azure Function + deploy suggestion endpoint

Provision Azure OpenAI + test prompt with sample data

Core Automation

Task - Effort

Project Created → Suggest Risks + LLM

Risk Created/Owner Changed → Notify Chain

query + LLM integration + citation and link

Monitoring + Resolution

Task - Effort

Hourly SLA Monitor (remind + escalate)

Weekly Summary Email

Resolution tracking flow (ResolvedDate, ClosedDate, root cause)

Quick Add form for custom risk capture

Dashboard + Polish

Task - Effort

connect to SharePoint,

SharePoint view formatting for list views

Embed dashboard in SharePoint project page | 30 min |

Testing + Go-Live

Task -Effort

End-to-end test: create project → accept risks → SLA check → escalate → resolve → close

Test with real PM + real owner emails

Documentation handoff

Production cutover

Post-Launch

When - What

Add more historical risk registers as they become available

Configure Power BI auto-email subscriptions

Review LLM accuracy. Tune prompts if needed.

Add more project types + departments as needed

Evaluate if custom risks warrant new historical categories

14. Success Criteria

Delivery (Go/No-Go)

-PM can create a project with name, type, department and get risk suggestions within 15 seconds

-LLM provides grounded analysis with clickable citations to source files

PM can accept, edit, and dismiss suggested risks

PM can add custom risks via Quick Add (30 seconds)

Risk owner receives email with [Update Status] and [Add Notes] buttons on assignment

Practice Lead is auto-looked up and CC'd correctly

SLA warnings fire at 4h (HIGH) / 12h (MEDIUM)

SLA breach escalates risk and notifies Owner + PM + PMO Lead

Activity (status change, any edit, acknowledge) satisfies SLA

Resolution time tracked from Accepted → Resolved

Closure form captures root cause and feeds Historical Risks

Weekly summary email sent Monday 8 AM

Power BI dashboard shows live data with 4 pages

All source citations link back to original Excel files

Requirements Needed

All historical risk registers consolidated into a single location or folder