## Sheet2
Project Type: AI Integration (Microsoft Copilot)
S/N​ | Risk Description​ | Impact (1-5)​ | Probability (1-5)​ | Rating (P X I)​ | Owner​ | Risk Response​
1​ | Delayed Delivery Online of Subscription​ | 5​ | TBD​ | TBD​ | Seamless HR​ | Shift​ commencement date of the implementation
2.​ | Involvement of Seamless HR in other projects/work related engagements​ | 4​ | TBD​ | TBD​ | Wragby​ | Prioritize involvement of assigned Seamless HR resources of the​ project
3.​ | Unavailability of Project Resource from WRAGBY​ | 5​ | 1​ | 5​ | Wragby​ | Assign replacement resources to the project.​
4.​ | Project Delay due to Client unavailability​ | 5​ | 1​ | 1​ | Seamless HR​ | Time and Material project costing would be applied for every extra day that the project resource have to spend till the project is completed and​ handed over.