## Sheet1
Project Type: Business Process Automation
Risk ID | Risk Description | Risk Category | Likelihood | Impact | Mitigation Strategy | Risk Owner
R001 | Delay in receiving project requirements | Schedule | High | High | Engage stakeholders early and set clear deadlines for requirements submission. Send reminders and escalate delays. | Punuka
R002 | Limited access to customer environment due to one deployment account | Resource/Access | High | High | Request multiple deployment accounts during planning. Test all logins prior to deployment. | Punuka
R003 | Lack of project prerequisites at kick-off | Planning | Medium | High | Introduce a project readiness checklist and verify all items before go-live. | Punuka
R004 | Delayed responses to required information | Communication | High | Medium | Define a communication matrix with timelines and escalation path. | Punuka
R005 | Limited sign-off rights from customer | Governance | High | High | Identify and assign alternate signatories at project inception. | Punuka
R006 | Insufficient Wragby resource allocation at project start | Resource | Medium | High | Allocate enough resources with back-up personnel identified in project plan. | Wragby
R007 | Pending integration with Digitslaw application | Technical | Medium | High | Agree on a shared development and integration timeline with technical leads from both sides. | Wragby/Punuka
R008 | Potential scope creep from unplanned feature requests | Scope | Medium | Medium | Implement strict change management process. All new requests must go through formal change control. | Wragby/Punuka
R009 | Dependency on third-party tools and configurations | External | Medium | Medium | Identify all third-party dependencies early. Include them in project timelines with agreed SLAs | Punuka
R010 | User adoption challenges post-deployment | User/Training | Medium | Medium | Conduct thorough user training and provide post-deployment support for 2–3 months. | Wragby
R011 | Delays in UAT due to unavailability of testers | Testing | Medium | Medium | Identify UAT testers and confirm their availability in advance. Lock in UAT calendar. | Punuka
R012 | Lack of stakeholder buy-in or support | Organizational | Low | High | Engage sponsors throughout the project with status updates and demos. | Wragby/Punuka