## Sheet1
Project Type: ERP Implementation (Microsoft Dynamics 365 BC)
Risk Description | Probability (H/M/L) | Impact (H/M/L) | Impact On | Owner | Mitigation Steps
Delay in provision of all requirements on project during the planning phase | H | H | Schedule | TEHC | Requirements should be provided as scheduled by the TEHC. Schedule will be rebaselined pending feedback on when these requirements will be provided. A cost and Material mode of payment will be activated to calculate for days lost
Scope creep | L | L | Schedule | TEHC/Wragby | Ensure requirements stays within the agreed scope for the engagement. A change management process will be activated
Unavailability of Key Project Stakeholders for reviews or feedback during the project cycle | H | H | Schedule | TEHC | The key project stakeholders are to indicate their buy in from the beginning of the project. A cost and material mode of payment will be activated to calculate for days lost
Unavailabilty of the required API and API requirements such as design document for integration where applicable | M | M | Scope & Schedule | TEHC | TEHC are to proactively engage third parties and ensure that the required APIs are provided before the required timeslot in the build phase. Delay in API provision will lead to Project schedule delays.
Delay in Project documentation Sign-off, documents such as SOW, Project Charter, FRD, Contract Letter | H | H | Scope & Schedule | TEHC | TEHC should ensure the project documents are signed off on time. Project will be on hold until documents are signed off and the build phase can commence.
Delayed Delivery or purchase of licenses | H | H | Schedule | TEHC/Wragby | Shift commencement date of the implementation
Unavailability of Project Resource from WRAGBY | H | H | Schedule | Wragby | Proactively assign replacement resource to the project.