## Sheet1
RISK REGISTER
Project Name | Microsoft Copilot Agents Implementation
Department | PMO
Customer Name | FIDELITY BANK
Stage Gate | ALL
Project Type | AI Implementation (Microsoft Copilot Agents for Enterprise Automation)
Risk ID | Risk Description | Risk Category | Likelihood | Impact | Risk Rating | Project Lifecycle Stage | Response Strategy | Risk Response Plan | Risk Owner | Status | Date Raised | Date Closed
R1 | Delayed delivery of SOPs, Data Dictionary & High-Level Requirements from Fidelity Bank teams | Dependency | High | High | High | Initiation & Planning | Mitigate | Escalated at weekly review; COB 10 Apr delivery confirmed for most items, balance by 14 Apr; Pedro Duru coordinated with Fidelity teams. | Ogazi Chikwendu / Pedro Duru | Closed | 2026-04-08 | 2026-04-10
R2 | Power Automate and Microsoft Copilot license provisioning delayed, blocking environment setup and requirements phase kick-off | Resource | Medium | High | Medium | Initiation & Planning | Escalate / Mitigate | Flagged as critical dependency; Fidelity IT engaged; escalation via Pedro Duru; monitor until license assignment and environment readiness. | Fidelity Bank IT / Pedro Duru | Closed | 2026-04-08 | 2026-04-24
R3 | Integration Requirements Call not held, risking architecture design start and SOW finalization | Schedule | High | Medium | High | Initiation & Planning | Mitigate | Rescheduled for 14 Apr and combined with Cloud Engineering call to reduce stakeholder overhead and accelerate open actions. | Pedro Duru | Closed | 2026-04-08 | 2026-04-14
R4 | Stakeholder register not received on time, delaying Project Charter submission and formal approval | Dependency | Medium | Medium | Medium | Initiation & Planning | Mitigate | Follow up with Modupe, Buchi and Suleiman; chase at COB until received; proceed immediately with Project Charter once submitted. | Modupe Fadare / Buchi / Suleiman | Closed | 2026-04-08 | 2026-04-17
R5 | CIO not yet available to approve AI & Business Strategy workshop dates, stalling strategy-stream activation | Dependency | Medium | Medium | Medium | Initiation & Planning | Mitigate | Obtain CIO availability; validate participant list with executive sponsors; keep technical delivery stream separate. | Ogazi Chikwendu | Closed | 2026-04-10 | 2026-04-17
R6 | Azure Landing Zone / Milestone 1 sign-off delayed beyond 4 May 2026, creating cascading impact on downstream phases | Schedule | Low | High | Low | Initiation & Planning | Mitigate | Weekly reviews and Friday check-ins; prepare sign-off documents ahead of milestone completion; early engagement with approvers. | Tomilayo Osho / Fidelity Bank UAT Lead | Closed | 2026-04-10 | 2026-05-04
R7 | Scope creep from additional use cases or integration requirements beyond the three approved use cases | Scope | Medium | High | Medium | Initiation & Planning | Avoid / Control | Maintain approved scope in Project Charter and SOW; enforce formal change control and sign-off for any additions. | Tomilayo Osho / Charles Faweya | Monitoring | 2026-04-10
R8 | EA Board review delays affecting build-phase start and architecture readiness | Governance | Medium | High | High | Initiation & Planning | Mitigate | Embed EA Board checkpoint into plan; use Ogazi confirmation that the board can accommodate review modifications. | Temitope Ajayi / William Bessa-Simons / Micheal Ojo | Monitoring | 2026-04-10
R9 | Signed SOW and Project Charter outstanding, blocking contracting and governance | Governance | High | High | High | Initiation & Planning | Mitigate | Drive approvals through project manager and sponsors; track signatures until both documents are received. | Fidelity Bank Project Manager | Closed | 2026-04-10 | 2026-04-14
R10 | Service account provisioning on ManageEngine pending full configuration despite account creation | Technical / Dependency | High | High | High | Build & Configuration | Mitigate | Continue daily follow-up; validate account access end-to-end before ITSM integration testing. | Fidelity Bank | Closed | 2026-04-20 | 2026-04-24
R11 | Delay in environment setup | Technical / Dependency | High | High | High | Build & Configuration | Mitigate / Escalate | Active escalation and daily follow-ups until environment readiness is validated. | Fidelity Bank | Closed | 2026-04-20 | 2026-05-04
R12 | Delay in provisioning Finacle Integration API | Technical / Dependency | High | High | High | Build & Configuration / Integration | Mitigate / Escalate | Daily escalation with Fidelity; developer validation once endpoints are released; sequence integration immediately after access is granted. | Fidelity Bank | Closed | 2026-04-20 | 2026-05-20
R13 | Delay in provisioning ITSM Integration API | Technical / Dependency | High | High | High | Build & Configuration / Integration | Mitigate / Escalate | Escalate missing authentication parameters and configuration ownership; continue daily follow-up until API support update is received. | Fidelity Bank | Closed | 2026-04-20 | 2026-05-14
R14 | Blockers impacting timelines prompted executive escalation | Dependency / Governance | High | High | High | Build & Configuration / Integration | Escalate | Maintain executive escalation and daily follow-up on Fidelity-owned integrations until blockers are cleared. | Fidelity Bank | Closed | 2026-04-20 | 2026-05-20
R15 | ITSM integration impeded by missing authentication parameters and unclear configuration ownership | Technical | High | High | High | Integration | Mitigate | Clarify authentication approach and ticket payload; validate endpoint access and fix configuration gaps before testing. | Fidelity Bank / Wragby | Closed | 2026-05-08 | 2026-05-14
R16 | Testing window reduction due to delays and public holiday, creating potential slip in target dates | Schedule | High | High | High | Integration & Testing | Mitigate | Compress plan, sequence QA/UAT tightly, front-load scripts and evidence preparation, and maintain executive visibility on milestone dates. | Fidelity Bank / Tomilayo Osho | Open | 2026-05-11
R17 | Concerns on external support capability / experience slowing issue resolution | Resource / Support | High | High | High | Integration & Testing | Mitigate | Escalate support needs and remove ambiguity on support ownership to avoid repeated blockers. | Fidelity Bank | Closed | 2026-05-11 | 2026-05-14
R18 | Staging access limitations slowing staging and deployment activities | Technical / Access | High | High | High | Integration & Testing / Deployment | Mitigate | Compile and send access requests; coordinate with stakeholders until staging access is granted. | Fidelity Bank | Closed | 2026-05-11 | 2026-05-26
R19 | FRD / BRD misalignment risking rework during testing | Quality / Scope | High | High | High | Integration & Testing | Mitigate | Run alignment session; update documentation and testing artefacts; secure agreement on expected behaviour before formal testing. | Fidelity Bank / Wragby | Closed | 2026-05-15 | 2026-05-18
R20 | IAM approval hierarchy not fully defined | Requirements / Governance | High | Medium | Medium | Build & Configuration | Mitigate | Obtain final approval hierarchy and integrate into IAM agent before closure milestones. | Fidelity Bank | Closed | 2026-05-15 | 2026-05-26
R21 | Delay due to missing ITSM service templates | Dependency / Technical | High | High | High | Integration & Testing | Mitigate | Request, receive and validate service templates to unblock deployment and test execution. | Fidelity Bank | Closed | 2026-05-15 | 2026-05-29
R22 | FRD and UAT sign-off pending from Fidelity Bank, impacting governance and go-live | Governance / Sign-off | High | High | High | Deployment & Go-Live | Mitigate / Escalate | Continue follow-up on signed FRD and UAT documents, summarise impact in weekly reporting, and escalate through sponsors where needed. | Fidelity Bank | Open | 2026-05-26 | 2026-05-31
R23 | Compressed timeline with parallel testing, integration and deployment increases coordination risk | Schedule / Delivery | High | High | High | Deployment & Go-Live | Mitigate | Use frequent stand-ups, explicit control points, and close coordination across Fidelity and Wragby to manage parallel streams. | Fidelity Bank / Wragby | Open | 2026-05-29
R24 | Production deployment remains dependent on completion of Fidelity Bank testing cycles and stakeholder approvals | Dependency / Schedule | High | High | High | Deployment & Go-Live | Mitigate | Track testing cycle completion and approvals as deployment entry criteria; maintain dependency log and sponsor visibility. | Fidelity Bank | Open | 2026-05-29 | 2026-06-10
R25 | Trial test plan / environment expiration in mid-June risks continuity of end-to-end collaboration and licensing justification | Resource / Licensing | Medium | High | Medium | Deployment & Go-Live | Mitigate | Complete end-to-end collaboration before expiry and secure post-trial licensing justification / extension. | Fidelity Bank / Microsoft / Wragby | Open | 2026-06-01 | 2026-06-15
R26 | Project behind schedule because end-user training should have started while integration and testing are still ongoing | Schedule | High | High | High | Enablement & Adoption | Mitigate | Re-baseline enablement sequence; complete testing and approvals before launching knowledge transfer and training. | Tomilayo Osho / Fidelity Bank | Open | 2026-06-09
R27 | Knowledge transfer cannot proceed until quality acceptance testing and user acceptance testing are completed and Fidelity Bank provides feedback | Dependency / Adoption | High | Medium | Medium | Enablement & Adoption | Mitigate | Gate KT on completion of QAT/UAT and documented feedback; request decision timelines explicitly in weekly reporting. | Fidelity Bank | Open | 2026-06-09
R28 | Awaiting feedback on UAT script alignment and required documentation from Fidelity Bank | Governance / Testing | High | Medium | Medium | Integration & Testing / Deployment | Mitigate | Coordinate with Pedro or Modupe to obtain required documentation; continue requesting timely feedback to maintain momentum. | Fidelity Bank / Tomilayo Osho | Open | 2026-06-09