## Sheet1
#VALUE!
Risk Scoring Criteria :
Impact (I): High, Medium, Low
Probability (P): High, Medium, Low
Risk Score: H/H = Critical, M/H = High, etc.
Response Strategies: Avoid, Mitigate, Transfer, Accept, Exploit
| Project Type: | Data Analytics / BI
ID | Risk Description | Category | Impact | Probability | Risk Score | Risk Response Strategy | Mitigation/Contingency Actions | Owner | Status
R001 | Delayed access to data sources and systems (e.g., MongoDB, ERPs, Excel, SFTP, APIs) | Technical | High | High | Critical | Mitigate | Send pre-kickoff prerequisite checklist requesting all credentials, server info, and access. Engage client early. | Tech Lead / PM | Open
R002 | Third-party managed systems may slow down data integration (e.g., MongoDB, ERP vendors) | External | High | Medium | High | Transfer | Escalate to client sponsor to facilitate vendor engagement. Schedule buffer time in plan. | PM | Open
R003 | Stakeholder has not procured required licences (Power BI Pro, Copilot, Azure, Windows Server) | Technical / Licensing | Medium | High | High | Mitigate | Add to prerequisites. Recommend Copilot to ease adoption. Follow up with procurement team. | PM / BA | Open
R004 | Lack of departmental stakeholder engagement or nomination of data/report owners | Stakeholder | High | High | Critical | Avoid | Escalate to NewCross leadership; require reps per department pre-kickoff. Make part of kickoff readiness. | PM / Sponsor | Open
R005 | Assigned resources unavailable or multitasked on other projects (e.g., Emmanuel, Mate) | Resource | High | High | Critical | Mitigate | Track weekly resource availability. Request full dedication for peak phases. Raise to PMO. | PM / Resource Mgr | Open
R006 | Data Engineer not yet onboarded (ETA July 17); gap in technical execution | Resource | High | High | Critical | Accept / Mitigate | Use interim backup team (Glory, Funke, Interns). Prioritize onboarding deliverables. Plan staggered dev start. | PM | Open
R007 | Unrealistic timeline (148 days) vs resource availability and dependencies | Schedule | High | High | Critical | Mitigate | Re-baseline project after WBS submission. Communicate revised timeline with supporting evidence. | PM | Open
R008 | Power BI adoption challenges by users unfamiliar with Fabric or Copilot | Change Management | Medium | Medium | Medium | Mitigate | Highlight during stakeholder workshop. Provide training and demo Copilot productivity tools. | BA / Trainer | Open
R009 | Historical lessons from AirPeace projects not applied (e.g., unclear access, late commercials) | Governance / Learning | Medium | Medium | Medium | Avoid | Apply lessons proactively in documentation and planning. List in lessons learned register. | PMO | Closed
R010 | Unclear or undocumented data dictionaries / ERDs from departments | Data / Documentation | Medium | Medium | Medium | Mitigate | Request documentation during requirements sessions. Define expected artefacts in checklist. | BA / Data Engineer | Open
R011 | Unclear ownership of business processes or KPIs per department | Stakeholder / Governance | Medium | Medium | Medium | Mitigate | Facilitate initial business mapping session; assign process owners for each domain. | PM / Sponsor | Open
R012 | SFTP setup for data exchange lacks configuration info (e.g., IP, port, encryption) | Technical / Security | High | Medium | High | Mitigate | Clarify and document SFTP prerequisites with client IT. Test pre-kickoff. Confirm encryption standards. | Security Lead / PM | Open
R013 | Project scope creep due to evolving reporting demands | Scope | Medium | Medium | Medium | Control | Lock scope in Project Charter. Use formal change request process post-scope freeze. | PM | Open
R014 | Incomplete or missing signed commercials before project start | Contractual | Medium | Medium | Medium | Avoid | Send commercials as separate from proposal. Delay start until signature. | Business Dev / PM | Open
R015 | Availability of non-technical staff for requirements elicitation (e.g., HR, Legal, Admin) | Stakeholder | Medium | Medium | Medium | Mitigate | Schedule flexibly. Use async questionnaires to gather inputs. Provide use-case demos. | BA | Open
R016 | Azure subscription delays for workspace deployment | Infrastructure | High | Medium | High | Mitigate | Add Azure subscription to prerequisite checklist. Confirm service availability. | Tech Lead / Client IT | Open
R017 | Several departments (Risk, G&G, Legal & Compliance, Administration) are yet to finalize their data capture strategy or platform, which may impact full integration timelines. | Organizational | High | Medium | High | Mitigate | Conduct stakeholder alignment workshops to expedite decisions. Escalate dependency risks during steering meetings. | PM / Business Analyst | Open