## Risk Register
EPIFL RISK REGISTER
Project Type: Cloud Infrastructure Deployment
ID | PLC | Date (mm/dd/yyyy) | RISK | MATERIALIZED RISK? | PROBABILITY 1-5 | IMPACT 1-5 | PI SCORE | RISK RANKING | IMPLICATION | RISK RESPONDA/MITIGATION | RESPONDA OWNER | EXPECTED RESPONDA IMPACT | ACTUAL RESPONDA | ACTUAL RESPONDA IMPACT | PROBABILITY 1-5 KEY | IMPACT 1-5 KEY
RSK001 | ALL PLC |  | Unavailability of delivery team due to Involvement in other projects/work related engagements, sickness, leave, resignation, contract expiration etc. | No | 4 | 4 | 16 | Very High | All | Plan the development with disruptions in mind. Negotiate with functional manager for a replacement resource Employ more resources | DA, PM | The project should not suffer from resource constraints
RSK002 |  |  | Realistic timeline is greater than budgeted timeline as a result of underestimated timeline in comparison to project scope | No | 4 | 4 | 16 | Very High |  | Include additional resource (Consider schedule crashing to save cost if possible) Raise change requests to reflect changes in timeline if the above mitigation are futile
RSK003 |  |  | Inaccurate estimated timelines provided during the schedule/sprint planning Sessions | No | 3 | 4 | 12 | High |  | Involve technical resource in sprint planning Session Involve another resource in the schedule/sprint planning to DArve as a quality check
RSK004 | Planning |  | Inability of client to provide accurate requirements | No | 3 | 4 | 12 | High | All | Ask probing and critical questions | BA, DA | The team will uncover requirements that were not initially mentioned, thus helping the team to develop a solution that aligns with the customer's expectation
RSK005 | Planning |  | Unavailability of stakeholders for requirement gathering, validation and review | No | 4 | 4 | 16 | Very High | Schedule | Delegate another team member to handle the Session and record the Session Raise a change request to request for the project to be moved/extended (This may incur cost) Prioritize involvement of assigned resources on the project | Customer | The project would run according to schedule
RSK006 | ALL PLC |  | Scope Creep. | No | 3 | 4 | 12 | High | All | Hold scope validation Session with the internal team and stakeholders team to align on understand. Get customer sign off on requirements Build to specification Raise change request if scope differs from original requirements | PM, DA | Project runs according to scope
RSK007 | Closure |  | Lack of adoption of the solution by the customer |  | 5 | 4 | 20 | Very High | Quality | Conduct online training Conduct offline/physical training Create a whatsapp group for quick resolutions of issues and request Develop a robust change management plan | Project Manager | Full Adoption of the system
RSK008 | ALL |  | Delays in signing off | No | 4 | 3 | 12 | High | Schedule | Continuous communication with the customer | Project Manager | Quicker sign off
RSK010 | Initiation |  | Delayed Delivery Online Subscription/licenses on Huawei | No | 3 | 5 | 15 | High | Schedule | Rescedule the commencement date of the implementation
RSK011 | ALL |  | Involvement of EPIFL & in other projects/work related engagements | No | 3 | 3 | 9 | Medium |  | Prioritize Involvement of assigned EPIFL & resources of the project
RSK012 | Execution |  | Unavailability of Project Resource from WRAGBY | No | 1 | 5 | 5 | Low |  | Assign replacement resources to the project.
RSK013 | Closure |  | Insufficient Training | No | 2 | 4 | 8 | Medium |  | Provide training post-implementation.