## Risk Register v2
First Independent Power Limited
Project Type: Cloud Infrastructure Deployment
ID | PLC | RISK | MATERIALIZED RISK? | PROBABILITY 1-5 | IMPACT 1-5 | PI SCORE | RISK RANKING | IMPLICATION | RISK RESPONSE/MITIGATION | RESPONSE OWNER | EXPECTED RESPONSE IMPACT | ACTUAL RESPONSE | ACTUAL RESPONSE IMPACT | PROBABILITY 1-5 KEY | IMPACT 1-5 KEY
RSK001 | ALL | Lack of deep experience with deploying resources on AWS | Yes | 2 | 5 | 10 | High | All | Seek the expertise of resources within Azure to help out. Seek the expertise of other members in Digital Advisory with experience in AWS. Contact the AWS account manager for direction Liaise with the Reddington account manager for direction | Daniel | Provide knowledge on how to resolve blockers | Response implemented | Provided clarity on the implementation
RSK002 | Planning | Possibility of underestimating or overestimating the the time and effort to complete the implementation | Yes | 3 | 3 | 9 | Medium | Schedule | Seek the support of the internal and external resources in estimating the work accurately. Do some research on the things to be done | Ife | More accurate estimation | Response implemented | Provided clarity on the implementation
RSK003 | Execution | Possibility of the customer not registering under our organization | No | 3 | 3 | 9 | Medium | Cost | Seek the expertise of the AWS and Reddington contact people Convince the customer on the need to sign up under our organization | Daniel, Ife | The customer would sign up under our organization | Response implemented | Cutomer signed up under our organization
RSK004 | ALL | Involvement of key resources in other projects | No | 2 | 4 | 8 | Medium | Schedule | Ensure dedicated resources are available, plan for resource allocation in advance | Daniel |  | Response implemented | Reduced the delays on the project
RSK005 | Execution | Scope creep leading to increased costs and extended timelines | Yes | 2 | 4 | 8 | Medium | Schedule | Strictly adhere to defined project scope Given the strategic plans for the customer, additional scope items that require minimal effort can be done. However, the number and scope must be limited | Daniel, Ife | Customer satisfaction minimal scope creep | Allowed some additional scope that required minimal effort
RSK006 | Closure | Customer's lack of readiness and understanding of solution deployed | No | 3 | 3 | 9 | Medium | Schedule | Provide comprehensive support and training to the customer, ensure readiness before migration Provide an As-Built document Share link to the training session for the customer's reference | Daniel | Customer would have an understanding of the solution | Response implemented | customer had a good understanding of the solution after the training
RSK007 | Controlling | Poor quality of deliverables not meeting customer expectations | No | 1 | 5 | 5 | Medium | Quality | Develop a solutions architecture document Ensure quality checks at every stage, align deliverables with customer expectations | Daniel, Ife | Improve quality of deliverables | Response implemented | Improved quality of deliverables
RSK008 | Closure | Delay in project closure due to customer's non-responsiveness | Yes | 4 | 2 | 8 | Medium | Cost | Decommission resources from the project Use different communication means to reach the customer - WhatsApp, Michael, Email, Phone call | Daniel | Save cost | Response implemented | Project closure

## Issues Log
ID | PLC | Risk ID | Issue | Status
IS001 | Execution | RSK004 | Unavailability of some of the support Project Resource from WRAGBY | Resolved
IS002 | Planning | NA | Delayed availability of stakeholders for requirement validation | Resolved
IS003 | Execution | NA | Delay in obtaining customer consent for changes to account structure | Resolved
IS004 | Execution | NA | Inadequate communication among project team and stakeholders | Resolved
IS005 | Execution | NA | VPN connectivity issues affecting project progress | Resolved
IS006 | Execution | NA | Non-responsiveness of key stakeholders (e.g., Nunayon) | Resolved
IS007 | Execution | NA | Issues with Sage server publishing and other technical requirements | Resolved
IS008 | Execution | NA | Complexity in the communication web among different teams and stakeholders | Resolved
IS009 | Closure | RSK008 | Delay in project closure due to pending approvals | Resolved