## Risk Register v2
ALBEN HEALTHCARE RISK REGISTER
Project Type: Cloud Infrastructure Deployment
ID | PLC | RISK | MATERIALIZED RISK? | PROBABILITY 1-5 | IMPACT 1-5 | PI SCORE | RISK RANKING | IMPLICATION | RISK RESPONSE/MITIGATION | RESPONSE OWNER | EXPECTED RESPONSE IMPACT | ACTUAL RESPONSE | ACTUAL RESPONSE IMPACT | PROBABILITY 1-5 KEY | IMPACT 1-5 KEY
R001 | ALL PLC | Involvement of the delivery team in other projects/work related engagements | Yes | 2 | 4 | 8 | Medium | All | Plan the development with disruptions in mind. | SE, PM | The project should not suffer from resource constraints
[9 empty] | 1 Deploy other resources to the project when primary resources is unavailable. 2 Begin to involve secondary resource in discussions and progress to ensure seamless transition if the time arrives | SE
[9 empty] | Employ more resources | Wragby
R002 | ALL PLC | Delayed completion of solution due to deployment of solution that does not meet the customer's requirements |  | 3 | 4 | 12 | High | Quality | Collect accurate requirements and validate each module before development | BA | The requirements will be properly validated before the development
[9 empty] | Review the requirements with the Wragby team before implementing | SE, PM
[9 empty] | Review development with the client before marking the module as done. | Development team (SE & PM)
[9 empty] | Build according to specification | SE
[9 empty] | Conduct proper test (Unit, regression) | SE
[9 empty] | Conduction proper internal user acceptance test before reviewing with the customer | Tester
[9 empty] | Utilize the Azure Board for storing requirements, and hold a session with all project team members to ensure there is a common understanding on how to use the board | Development team
R003 | Planning | Inability of client to provide accurate requirements | Yes | 4 | 4 | 16 | Very High | All | Ask probing and critical questions | BA, SE | The team will uncover requirements that were not initially mentioned, thus helping the team to develop a solution that aligns with the customer's expectation
R004 | Planning | Delayed availability of stakeholders for requirement validation | Yes | 3 | 4 | 12 | High | Schedule | Delegate another team member to handle the session and record the session | SE | The project would run according to schedule
[9 empty] | Raise a change request to request for the project to be moved/extended (This may incur cost) | Alben
R005 | ALL PLC | Unavailability of Project Resource from WRAGBY | Yes | 2 | 4 | 8 | Medium | All | Delegate another team member in case of absence | SE/PMO (Wragby) | The project would run according to plan
R006 | ALL PLC | Involvement of Alben Healthcare in other projects/work related engagements |  | 3 | 4 | 12 | High | Schedule | Prioritize involvement of assigned resources on the project | Wragby delivery team | Project runs according to schedule
[9 empty] | Deploy additional resources on the TNK project. | SE
R007 | Execution | Possibility of not providing a significant increment by the end of the sprint | Yes | 4 | 4 | 16 | Very High | Schedule | Review validated requirements and commence development immediately | SE, BA | Usable increment is available as at schedule
[9 empty] | Resources need to prioritize portfolio and ensure that a usable increment is available as at when scheduled | SE
R008 | ALL PLC | Scope Creep. |  | 4 | 4 | 16 | Very High | All | Emphasize the scope listed out in the requirement to the customer | PM | Project runs according to scope
[9 empty] | Build to specification | SE
R009 | Execution | The deployment of relatively new/different resources on the project could lead to further delays in development as a result of the resources' unfamiliarity with the product |  | 3 | 4 | 12 | High | Schedule | Ensure proper hand-holding sessions are held with the deployed resources. | SE
[9 empty] | Developers familiar with the solution should ensure proper monitoring of the development work of the resources | SE
[9 empty] | Estimate progress periodically to ensure we can still meet up with timelines (Check progress on DevOps) | SE, PM
[9 empty] | Communicate any issues that could lead to delays proactively | SE
[9 empty] | Manage the customer by giving assurances and estimated timelines, and ensuring the team can meet up to the provided time | PM
Possibility of installing the OS and it does not capture the existing volumes.

## Issues Log
ID | PLC | Risk ID | Issue | Status | Date (dd/mm/yyyy) | Resolution Date
IS001 | Execution | R001 | Nick unable to take remote access of Papa's screen due to group policies | Active | 2024-03-07
issue with ip block already in use