## Sheet1
RISK REGISTER
Document Name | Risk Register
Department | Digital Advisory
Customer Name | NHIA
Stage Gate | Planning
Project Type | Cloud Migration
Risk ID | Risk Description | Risk Category | Likelihood | Impact | Risk Rating | Project Lifecycle Stage | Response Strategy | Risk Response Plan | Risk Owner | Status
R1 | Delay in provisioning AWS accounts and granting access to the relevant teams for each workload environment. | Technical / Access Management | Low | High | High | Deployment Preparation | Mitigate | Define access requirements early and create AWS accounts ahead of workload deployment. Ensure all required users and teams are granted access before migration begins. | Cloud Infrastructure Team | Open
R2 | Additional stakeholders or external vendors may require access to the environment that was not initially identified, which could cause delays or security concerns. | Security / Access Control | Medium | Medium | Medium | Planning / Deployment | Mitigate | Document all stakeholders requiring access and implement a structured access request and approval process before provisioning credentials. | Project Manager / Infrastructure Team | Open
R3 | Lack of clear responsibility boundaries between the infrastructure team and application teams may delay application deployment after infrastructure provisioning. | Project Management / Coordination | Medium | High | High | Deployment | Mitigate | Clearly document roles and responsibilities. Ensure application teams are aware that infrastructure provisioning is in scope while application deployment is their responsibility. | Project Manager | Open
R4 | Potential unidentified dependencies between workloads or shared resources may cause issues during migration if discovered later. | Technical / Architecture | Low | High | Medium | Planning | Mitigate | Conduct additional verification with stakeholders to confirm whether any shared databases, APIs, or integrations exist between workloads. | Solution Architect | Open
R5 | The proposed architecture is currently high-level and has not yet been fully validated by stakeholders. Changes after approval could affect timeline and cost. | Architecture / Scope | Medium | Medium | Medium | Design | Mitigate | Share architecture diagrams with stakeholders for early review and obtain formal confirmation before implementation begins. | Solution Architect / Project Manager | Open
R6 | Some infrastructure or system requirements may not have been captured during the initial estimation phase and could affect project scope or cost. | Scope / Financial | Medium | Medium | Medium | Planning | Mitigate | Reconfirm workload requirements with stakeholders and update the scope or estimate if additional resources are required. | Project Manager | Open
R7 | Uncertainty regarding the migration approach for websites currently hosted in the GBB data center using cPanel and WHM. Migration compatibility needs confirmation. | Technical / Migration | Medium | Medium | Medium | Migration | Mitigate | Validate cPanel migration compatibility with AWS Marketplace cPanel setup and test migration process before full migration. | Infrastructure Team | Open
R8 | Key technical resources assigned to the NHIA cloud migration project are also allocated to multiple ongoing projects, which may affect their availability and lead to delays in completing project tasks or deliverables. | Resource / Staffing | High | High | High | Planning / Deployment | Mitigate | Develop a clear resource allocation plan and confirm availability with functional managers. Prioritize critical tasks, schedule activities in advance, and identify backup resources where possible to reduce potential delays. | Project Manager | Open
R9 | Planned cutover downtime required when SQL license is applied (server restart). | Technical / Migration | High | Medium | Medium | Migration | Communicate | Communicate downtime in advance. Schedule cutover over the weekend to minimize effect. Conduct pre-cut over checks