## Risk Register
RISK REGISTER
Project Name: |  | Microsoft Sentinel
Project Manager Name: |  | Tomilayo Osho
Project Ref: |  | ACCÈSBANQUE Madagascar
Project Type: |  | Cybersecurity Implementation
Risk ID | Risk Description | Risk Category | Likelihood | Impact | Risk Rating | Project Lifecycle Stage | Response Strategy | Risk Response Plan | Risk Owner | Status
R1 | Azure Plan Subscription restricted in Madagascar | Project Management | Medium | High | Medium | Planning | Mitigate | Contacted Microsoft For Enterprise Agreement, Stakeholder Required to make use of Pay-as-you-go Plan. Ensure to carryout appropriate checks to ensure all licenses are available before commencement of the project. | AB Madagascar | Closed
R2 | Microsoft Defender XDR Licenses not available | Organizational | Medium | Medium | Medium | Execution | Mitigate | Foster a culture of open communication and collaboration, emphasizing the benefits of agile delivery. | AB Madagascar | Active
R3 | Stakeholder delay in providing required documents | Stakeholder | Medium | High | Moderate | Planning | Mitigate | Proactively follow up with stakeholders to ensure timely document submission | Project Manager | Closed
R4 | Delayed Delivery Online Subscription/licenses | Technical | High | High | Critical | Deployment | Mitigate | Shift commencement date of the implementation | ACCÈSBANQUE Madagascar. | Closed
R5 | Involvement of ACCÈSBANQUE Madagascar. in other projects/work related engagements | Technical | Medium | Medium | Moderate | Deployment | Mitigate | Prioritize Involvement of assigned ACCÈSBANQUE Madagascar. resources of the project | ACCÈSBANQUE Madagascar. | Closed
R6 | Scope Creep | Technical | Medium | High | Moderate | Deployment | Mitigate | A standard Change Control Process will be in place to handle this | ACCÈSBANQUE Madagascar./Wragby | Closed
R7 | Unavailability of Project Resource from WRAGBY | Technical | Medium | High | Moderate | Deployment | Mitigate | Assign replacement resource to the project. | Wragby | Closed
R8 | Project Delay due to Client unavailability or client induced factors | Technical | Medium | High | Moderate | Deployment | Mitigate | Credentials to be shared via a secure link to be created to one person at a time | ACCÈSBANQUE Madagascar. | Closed
R9 | Limited expertise with Microsoft Sentinel | Technical | Medium | High | Moderate | Deployment | Mitigate | Tailored training sessions for security team | ACCÈSBANQUE Madagascar. | Closed
R10 | Access Delay leading to project timeline extension | Technical | Medium | High | Moderate | Deployment | Mitigate | Assign bank-side point of contact for prompt access approval | ACCÈSBANQUE Madagascar | Closed
R11 | High alert volume leading to alert fatigue for the for the security team | Technical | Medium | High | Moderate | Deployment | Mitigate | Tune alert thresholds, conduct periodic alert reviews, establish escalation processes | ACCÈSBANQUE Madagascar./Wragby | Closed
R12 | Stakeholder removed Wragby Technical Team Access to the System during deployment | Technical | High | High | Moderate | Deployment | Mitigate | Establish clear access protocols in the project agreement, including escalation processes and stakeholder commitments to maintain technical team access during deployment. | ACCÈSBANQUE Madagascar./Wragby | Closed
R13 | Stakeholder lacks sufficient understanding of project scope and configurations despite active participation in configuration sessions and video calls. | Technical | High | High | Moderate | Deployment | Mitigate | Provide simplified documentation, periodic walkthroughs, and a dedicated Q&A session to enhance stakeholder comprehension and engagement | ACCÈSBANQUE Madagascar./Wragby | Closed
| Delayed reviews and late-stage amendments disrupt project timelines, increase costs, and risk misalignment, making early alignment and timely feedback critical to project success | Project Management | Medium | High | Medium | Planning | Mitigate | Establish clear deadlines, enforce a formal change management process, and communicate the impact of delays to ensure timely stakeholder feedback and alignment. | ACCÈSBANQUE Madagascar
| Leaving the project open for a single issue extends timelines, increases costs, and affects resource planning | [6 empty] | Resolving this issue during the free support phase ensures timely project closure, cost efficiency, and optimal resource utilization | ACCÈSBANQUE Madagascar