## Risk Register
RISK REGISTER
Project Name: |  | Microsoft Sentinel
Project Manager Name: |  | Tomilayo Osho
Project Ref: |  | AB RWANDA
Project Type: |  | Cybersecurity Implementation
Risk ID | Risk Description | Risk Category | Likelihood | Impact | Risk Rating | Project Lifecycle Stage | Response Strategy | Risk Response Plan | Risk Owner | Status
R1 | Delayed Delivery Online Subscription/licenses | Project Management | High | Medium | High | Implementation | Mitigate | Shift commencement date of the implementation | AB RWANDA. | Closed
R2 | Involvement of AB RWANDA. in other projects/work related engagements | Organizational | Medium | High | Medium | Planning | Mitigate | Prioritize Involvement of assigned AB RWANDA. resources of the project | AB RWANDA. | Closed
R3 | Scope Creep | Project Management | Medium | Medium | Medium | Implementation | Mitigate | A standard Change Control Process will be in place to handle this | AB RWANDA./Wragby | Closed
R4 | Unavailability of Project Resource from WRAGBY | Project Management | Medium | Medium | Medium | Implementation | Mitigate | Assign replacement resource to the project. | Wragby | Closed
R5 | Project Delay due to Client unavailability or client induced factors | Organizational | Medium | Medium | Medium | Implementation | Mitigate | Credentials to be shared via a secure link to be created to one person at a time | AB RWANDA. | Closed
R6 | Limited expertise with Microsoft Sentinel | Project Management | Medium | Medium | Medium | Implementation | Mitigate | Tailored training sessions for security team | AB RWANDA. | Closed
R7 | Access Delay leading to project timeline extension | Project Management | Medium | Medium | Medium | Implementation | Mitigate | Assign bank-side point of contact for prompt access approval | AB RWANDA. | Closed
R8 | High alert volume leading to alert fatigue for the for the security team | Project Management | Medium | Medium | Medium | Implementation | Mitigate | Tune alert thresholds, conduct periodic alert reviews, establish escalation processes | AB RWANDA./Wragby | Closed
R9 | Delayed Project Closure Document Signoff | Project Management | Medium | Medium | Medium | Closure | Mitigate | Communicate with the stakeholder highlighting the risks of delayed project closure | AB RWANDA | closed