## Risk Register
RISK REGISTER
Project Name: |  | Microsoft Defender for Endpoint
Project Manager Name: |  | Tomilayo Osho
Project Ref: |  | Delifrost
Project Type: |  | Cybersecurity Implementation
Risk ID | Risk | Risk Description | Likelihood | Impact | Risk Rating (Likelihood x Impact) | Mitigation Strategy | Risk Owner | Stakeholder Owner | Triggers/Indicators | Contingency Plan | Residual Risk | Status
R1 | Lack of Documentation from Sales Team | Inadequate or missing documentation from the sales team could delay project initiation and lead to misaligned expectations with the stakeholder. | High | High | 16 | Work closely with the sales team to request documentation, such as signed agreements, scope of work, and initial engagement notes. Follow up on outstanding deliverables and escalate if necessary. | Project Manager | Sales Team | Project initiation delayed or incomplete due to missing documents | Conduct a preliminary discovery session with the stakeholder to bridge documentation gaps temporarily. | Medium | Open
R2 | Licensing Mismatch | Incorrect or inadequate licensing for Microsoft Defender for Endpoint could result in partial functionality or missed features. | High | High | 16 | Ensure correct licenses are purchased based on organizational needs and confirm with the vendor. | Project Manager, Sales Team | Stakeholder (Finance/Procurement) | Incomplete license audit or misalignment during purchase | Review licensing periodically; escalate to vendor for adjustments. | Low | Open
R3 | Subscription Expiry/Changes | Subscription expiration or changes during the implementation phase. | Medium | High | 12 | Set reminders for renewal and ensure subscription terms cover the full implementation period. | IT Operations, Finance | Stakeholder (Finance/Procurement) | Subscription nearing expiration or payment delays | Ensure automatic renewal or budget allocation for extensions. | Low | Open
R4 | Over/Under Subscription | Misalignment in the number of endpoints covered under the subscription (over/under-subscribed). | Medium | Medium | 9 | Conduct a detailed audit of all endpoints before purchasing subscriptions and adjust licenses as necessary. | IT Operations, Project Manager | Stakeholder (Business Unit) | Number of endpoints increases or decreases during implementation | Regularly reassess endpoint needs and adjust subscription accordingly. | Low | Open
R5 | Compatibility Issues | Microsoft Defender may not be compatible with legacy systems or third-party software in use. | Medium | High | 12 | Perform system audits and pre-deployment testing for compatibility with Microsoft Defender. | IT Operations, Technical Lead | Stakeholder (Operations/IT) | Test environments showing compatibility failures | Plan for system upgrades or exclusions; escalate to vendor if unresolved. | Medium | Open
R6 | Performance Degradation | Defender could degrade system performance on older devices or devices with limited resources. | Medium | Medium | 9 | Review system requirements, upgrade hardware if needed, and optimize configurations to minimize performance impact. | IT Operations, Technical Lead | Stakeholder (Operations/IT) | Slow system performance during testing phase | Reconfigure Defender settings or replace outdated hardware. | Low | Open
R7 | Network Configuration Issues | Incorrect network configuration could affect communication between Defender and endpoints. | Medium | High | 12 | Ensure correct network configurations, including firewall and proxy settings, are in place before deployment. | Network Team, Technical Lead | Stakeholder (Network Operations) | Errors in network setup or communication failures | Set up network tests and validations; troubleshoot network issues. | Medium | Open
R8 | Integration Delays/Failures | Delays or failures in integrating Microsoft Defender with existing security tools or systems. | Medium | High | 12 | Plan and test integrations in phases, seeking assistance from Microsoft support or certified partners. | Project Manager, IT Operations | Stakeholder (Operations/IT) | Integration not working as expected in testing phase | Prioritize integration troubleshooting; engage support for issue resolution. | Medium | Open
R9 | Incorrect Configuration | Misconfiguration during deployment leading to missed security features or vulnerabilities. | Medium | High | 12 | Validate configurations during the pilot phase using best practice guidelines and test thoroughly. | Technical Lead, IT Operations | Stakeholder (Security/Compliance) | Misconfigurations during test or pilot phases | Create automated configuration checks and revalidate before full deployment. | Medium | Open
R10 | Resistance to Change | Employees may resist using the new security solution, leading to incomplete deployment or non-compliance. | High | Medium | 12 | Implement a comprehensive user adoption plan with training and communication strategies. | Project Manager, HR | Stakeholder (HR/Operations) | User feedback or survey results indicating resistance | Hold more training sessions, and establish user champions for advocacy. | Low | Open
R11 | Training Gaps | Lack of proper training for administrators or users, leading to mismanagement of security settings or missed alerts. | Medium | High | 12 | Provide detailed training for IT administrators and end-users, and create user-friendly guides. | HR, Project Manager | Stakeholder (HR/Operations) | Lack of training feedback or high error rates from users | Schedule additional training or hands-on workshops. | Medium | Open
R12 | Non-compliance with Regulations | Microsoft Defender may not meet regional data privacy and security regulations (GDPR, CCPA, HIPAA). | Medium | High | 12 | Perform a compliance audit to ensure the solution aligns with regulatory requirements. | Compliance Officer, Legal | Stakeholder (Legal) | Legal teams flag non-compliance issues | Engage legal for compliance guidance and adjust configurations. | Medium | Open
R13 | Data Handling and Storage Issues | Microsoft Defender not properly aligned with organization’s data retention policies. | Low | High | 8 | Configure Defender in alignment with organizational data retention policies, auditing regularly. | Data Privacy Officer, Technical Lead | Stakeholder (Compliance/Legal) | Data logs or storage exceeding retention limits | Update retention policies or review data usage periodically. | Low | Open
R14 | Vendor Support Delays | Delays in vendor support (Microsoft or third-party) impacting troubleshooting and implementation. | Medium | Medium | 9 | Establish clear communication channels with Microsoft and third-party vendors. Maintain a record of support requests for timely resolution. | Project Manager, IT Operations | Stakeholder (Vendor Management) | Vendor response time exceeding expectations | Escalate issues to vendor management and plan for backup solutions. | Low | Open
R15 | Dependency on Vendor Roadmap | Changes in Microsoft’s product updates, features, or licensing terms affecting the project. | Medium | Medium | 9 | Stay updated on product roadmaps and have contingency plans in place for delays or changes. | Project Manager, IT Operations | Stakeholder (Operations/IT) | Vendor roadmap delays or feature cancellations | Adjust project timelines or adapt to available features. | Low | Open
R16 | Targeted Cyberattacks During Deployment | Cyberattacks during the deployment phase could expose vulnerabilities or data. | Low | High | 8 | Implement interim cybersecurity measures during deployment and ensure full system protection. | Security Team, IT Operations | Stakeholder (Security Team) | Attack or data breach during deployment | Launch incident response plan and notify relevant stakeholders. | Low | Open
R17 | Budget Overruns | Unexpected costs due to resource allocation, licensing adjustments, or remediation efforts. | Medium | High | 12 | Maintain a detailed project budget, factoring in potential costs and include contingency funds. | Project Manager, Finance | Stakeholder (Finance) | Budget overruns due to unforeseen issues | Reallocate resources or adjust the scope to align with the budget. | Medium | Open
R18 | Project Delays | Delays in any phase of the implementation process could affect overall project timelines. | Medium | High | 12 | Monitor project progress regularly and implement proactive risk management practices. | Project Manager | Stakeholder (All) | Delay in any milestone or task | Adjust the project timeline and allocate resources to catch up. | Medium | Open