## Risk Log
NESTOIL RISK REGISTER
Project Type: Disaster Recovery / Business Continuity
ID | PLC | Date (mm/dd/yyyy) | RISK | MATERIALIZED RISK? | PROBABILITY 1-5 | IMPACT 1-5 | PI SCORE | RISK RANKING | IMPLICATION | RISK RESPONSE/MITIGATION | RESPONSE OWNER | EXPECTED RESPONSE IMPACT | ACTUAL RESPONSE | ACTUAL RESPONSE IMPACT | PROBABILITY 1-5 KEY | IMPACT 1-5 KEY
RSK001 | ALL PLC |  | Unavailability of delivery team due to Involvement in other projects/work related engagements, sickness, leave, resignation, contract expiration etc. | No | 3 | 4 | 12 | High | All |  | PM | The project should not suffer from resource constraints
RSK002 | ALL |  | Realistic timeline is greater than budgeted timeline as a result of improperly scoped requirements or issues | Yes | 4 | 4 | 16 | Very High |  | Include additional resource (Consider schedule crashing to save cost if possible)
RSK007 | ALL PLC |  | Scope Creep. | No | 3 | 4 | 12 | High | All | Hold scope validation session with the internal team and stakeholders team to align on understand. | PM | Project runs according to scope
| Initiation |  | Delayed Delivery Online Subscription/licenses | No | 3 | 5 | 15 | High
| Execution |  | Hardware/Network compatibility Issues | Yes | 3 | 5 | 15 | High |  | Conduct pre-deployment checks thoroughly.
| Execution |  | Software Compatibility |  | 3 | 4 | 12 | High |  | Validate compatibility before installation.
| Execution |  | Backup Job Failure | No | 3 | 5 | 15 | High |  | Test all configurations in a controlled setup
| Execution |  | Involvement of Nestoil Group & Veeam in other projects/work related engagements | No | 3 | 4 | 12 | High |  | Prioritize Involvement of assigned Nestoil Group & Veeam resources of the project
| Execution |  | Unavailability of Project Resource from WRAGBY | No | 3 | 3 | 9 | Medium |  | Assign replacement resources to the project.
| Execution |  | Downtime during setup |  | 1 | 5 | 5 | Medium |  | Schedule backups outside peak hours
| Execution |  | Data security breaches | No | 2 | 5 | 10 | High |  | Enable encryption and access controls
| Execution |  | Storage capacity issues | Yes | 2 | 5 | 10 | High |  | Implement Azure blob storage
RSK012 | ALL |  | Delays in signing off | Yes | 4 | 3 | 12 | High | Schedule | Continuous communication with the customer | Project Manager | Quicker sign off
RSK014 |  |  | Extension of project timeline | Yes | 5 | 4 | 20 | Very High | Schedule |  | Wragby

## Issues Log
ID | Issues | Impact | Impact Description | Status | Owner | Details
1 | Delay in the installation of Window OS servers | 5 | 14 days delay to project schedule | Completed | Nestoil
2 | Delay in reviewing and signing off project documentations | 4 | Gaps in understanding project quality, scope & expectations | In Progress | Nestoil
3 | Delay in the installation of the Veeam software due to issues with SQL server and physical storage | 4 | 2 days delay to project schedule | Completed | Nestoil
4 | Issues with installation of Veeam enterprise manager | 5 | Delay on project schedule | In progress | Veeam
5 | Issues with domain connectivity | 5 | Delay on project schedule | In progress | Nestoil | error message: Failed to connect to host