## Risk Register
Risk ID | Risk | Risk Description | Likelihood | Impact | Risk Rating (Likelihood x Impact) | Mitigation Strategy | Risk Owner | Stakeholder Owner | Triggers/Indicators | Contingency Plan | Residual Risk | Status
ORG001 | Construction Automation Feasibility | Limited stakeholder readiness, infrastructure, and integration challenges | 4 | 4 | 16 | Early engagement with construction teams, phased implementation | Project Manager | Construction SME | Delays in assessment feedback, resistance from teams | Extend assessment timeline, engage external consultants | Medium | Open
ORG002 | Software Assessment & Advisory | Poor software fit for business needs due to inadequate requirements gathering | 3 | 5 | 15 | Conduct detailed business requirement sessions, involve key users | Business Analyst | IT Leadership | Misalignment of proposed solutions with business processes | Reassess software choices, adopt phased rollout | Medium | Open
ORG003 | E-commerce Architecture & Implementation | High complexity in designing an end-to-end scalable system | 5 | 4 | 20 | Engage experienced architects, conduct proof-of-concept | IT Architect | Business Units | Slow progress in initial design phases, unclear requirements | Redefine scope, leverage MVP approach | High | Open
ORG004 | Zero Trust Policy & Access Control | Gaps in policy enforcement, resistance to security changes | 4 | 4 | 16 | Conduct security awareness training, implement phased rollout | Security Lead | IT Security | Unauthorized access incidents, lack of compliance | Strengthen monitoring controls, enforce strict access policies | Medium | Open
ORG005 | Sage Implementation Value Realization | Stakeholder adoption challenges, lack of ROI visibility | 3 | 5 | 15 | Early user training, clear KPIs for success tracking | ERP Team | Finance & Operations | Low user adoption, process inefficiencies | Engage Sage experts, improve change management | Medium | Open
ORG005A | SAGE Transition to Phase 1 | Stakeholder Finance ED requested postponement to April 2025, impacting Phase 0 closure | 4 | 4 | 16 | Align project timelines, ensure early Phase 1 engagement | Project Manager | Finance ED | Delays in Phase 1 initiation | Adjust resource allocation to Phase 1 priorities | Medium | Open
ORG006 | Role-Based Access Control (RBAC) | Delays in defining clear roles and privileges | 3 | 4 | 12 | Define roles early, ensure stakeholder involvement | Security Team | HR & IT | Inconsistent access rights, security breaches | Implement interim access controls | Low | Open
ORG007 | Data Platform & Analytics | Poor data quality, lack of structured governance | 4 | 5 | 20 | Define clear data governance policies, conduct data cleansing | Data Governance Lead | Business Intelligence | Inconsistent reports, inaccurate decision-making | Strengthen governance frameworks, automate data validation | High | Open
ORG008 | IT Governance Framework Development | Lack of alignment with business goals and industry standards | 3 | 5 | 15 | Align framework with COBIT, ISO standards, and risk frameworks | Governance Lead | Executive Management | Non-compliance with governance policies | Adjust framework to evolving needs | Medium | Open
ORG009 | Policy, Process & Procedure (PPP) Development | Resistance to new governance processes and policies | 3 | 4 | 12 | Conduct change management workshops, involve leadership | Risk & Compliance | Business Units | Delayed policy adoption, operational inefficiencies | Rollout in phases, reinforce through training | Medium | Open
ORG010 | Risk Assessment & Management | Lack of structured risk identification and mitigation | 3 | 5 | 15 | Establish risk governance, periodic risk reviews | Risk Manager | IT & Business Leaders | Unidentified risks leading to project delays | Escalate risks, conduct frequent risk audits | Medium | Open
ORG011 | Training & Awareness on Governance | Lack of awareness and understanding among employees | 4 | 3 | 12 | Conduct targeted training programs, gamify learning | Learning & Development | HR & Compliance | Low participation in training, frequent policy violations | Mandate training completion for key personnel | Low | Open
ORG012 | Delayed Information Provisioning | Stakeholder delays in providing necessary data to SMEs | 4 | 5 | 20 | Increase follow-ups, set firm deadlines with escalation process | Project Manager | Stakeholders | SMEs report lack of information | Implement stricter deadlines and accountability measures | High | Open
ORG013 | Incomplete Information from Stakeholders | Stakeholders providing partial or inaccurate data, hindering full assessment | 4 | 5 | 20 | Require structured documentation submissions, conduct validation sessions | Project Team | Stakeholders | Inconsistent or missing data affecting assessments | Establish a review and approval checkpoint before proceeding | High | Open

## Business Architecture Risk
Business Architecture Domain - Resource & Capability Risks
Project: Managed Technology Advisory Services – Origin Group
Project Type: | Managed Services
EXECUTIVE SUMMARY
This risk register identifies critical risks associated with the Business Architecture domain due to the absence of a dedicated Business Architect and reliance on a hybrid team structure with competing priorities and capability gaps.
Risk ID | Risk Title | Category | Description | Root Cause | Probability | Impact | Risk Score | Risk Level | Triggers | Risk Owner | Response Strategy | Recommended Actions | Recommended Contingency | Status
BA-001 | Absence of Dedicated Business Architect | Resource/Staffing | Project lacks dedicated Business Architect, creating critical capability gap in enterprise architecture definition, business process modeling, and strategic alignment | • Organizational resource constraints • Specialized skill shortage • Budget limitations | High (80%) | High | 16 (4×4) | CRITICAL | • Complex BA deliverables required • Stakeholder enterprise-level analysis requests • Integration with existing systems | Project Manager | MITIGATE | Recommend: Secure external BA consultant or internal BA resource allocation | Recommend: Emergency procurement of BA services through approved vendors | OPEN
BA-002 | Senior BA Role Transition Impact | Resource/Capability | Senior Business Analyst transitioned to Product Manager, creating knowledge gaps and reduced availability for senior-level BA activities | • Role transition without proper handover • Competing priorities in new role • Lack of succession planning | High (70%) | Medium-High | 12 (4×3) | HIGH | • Senior-level analysis requirements • Complex process modelling • Senior stakeholder engagement needs | Project Manager | MITIGATE | Recommend: Formalize time allocation agreement with Product Manager for BA activities | Recommend: Engage temporary external senior BA support | OPEN
BA-003 | GRSC Manager Multi-Domain Conflict | Resource/Competing Priorities | GRSC Manager working simultaneously on Cybersecurity and IT Governance, creating priority conflicts and availability issues | • Resource over-allocation • Lack of priority framework • Insufficient domain specialization | Medium-High (60%) | Medium | 9 (3×3) | MEDIUM | • Competing deadline pressures • Cybersecurity incidents • Governance implementation milestones | Resource Manager | MITIGATE | Recommend: Establish executive-level priority framework and resource allocation guidelines | Recommend: Approve temporary additional resources for competing domains | OPEN
BA-004 | Junior BA Experience Limitations | Skills/Capability Gap | Junior Business Analyst lacks experience for complex BA tasks, potentially causing quality issues and stakeholder concerns | • Insufficient training and development • Lack of mentorship • Complex requirements beyond skill level | Medium (50%) | Medium | 6 (2×3) | MEDIUM | • Complex process analysis requirements • Senior stakeholder presentations • Architecture decision scenarios | Project Manager | MITIGATE | Recommend: Approve external mentorship program and accelerated training budget | Recommend: Authorize immediate external BA support for complex activities | OPEN
BA-005 | Institutional Knowledge Loss | Knowledge Management | Critical BA knowledge may be lost due to team changes and lack of dedicated BA expertise continuity | • Poor knowledge management practices • Team composition instability • Insufficient documentation | Medium (40%) | High | 12 (3×4) | HIGH | • Team member transitions • Complex business rule interpretations • Historical decision rationale needs | Project Manager | MITIGATE | Recommend: Invest in comprehensive knowledge management system and documentation processes | Recommend: Engage external experts for knowledge recovery and documentation | OPEN
BA-006 | Deliverable Quality Degradation | Quality/Technical | Suboptimal BA deliverables due to skill gaps and resource constraints affecting project outcomes | • Inadequate review processes • Lack of BA standards • Insufficient quality gates | Medium-High (65%) | High | 12 (3×4) | HIGH | • Stakeholder feedback on quality • Failed deliverable reviews • Rework requirements | Project Manager | MITIGATE | Recommend: Approve external quality assurance and independent BA reviews | Recommend: Authorize scope adjustments or additional resources for quality remediation | OPEN
BA-007 | Stakeholder Confidence Erosion | Stakeholder/Communication | Reduced stakeholder confidence due to BA team capability concerns and deliverable quality issues | • Visible team composition issues • Previous quality concerns • Communication gaps | Medium (45%) | Medium-High | 9 (3×3) | MEDIUM | • Stakeholder complaints • Reduced engagement levels • Escalation to senior management | Project Manager | MITIGATE | Recommend: Executive communication strategy and visible commitment to addressing BA challenges | Recommend: Commission independent BA assessment to demonstrate commitment to quality | OPEN
BA-008 | Schedule Impact Cascade | Schedule/Dependencies | BA domain delays cascading to dependent project activities and overall timeline | • Critical path dependencies • Resource bottlenecks • Integration requirements | High (75%) | Medium-High | 12 (4×3) | HIGH | • BA milestone delays • Dependent activity holds • Integration timeline pressure | Project Manager | MITIGATE | Recommend: Approve additional resources for fast-tracking and parallel execution | Recommend: Authorize schedule baseline revision and additional budget for acceleration | OPEN
RISK MONITORING AND CONTROL
Key Risk Indicators (KRIs)
Business Architecture deliverable quality scores
Stakeholder satisfaction ratings on BA outputs
Schedule variance on BA-related tasks
Resource availability metrics
Knowledge transfer completion rates