## Inactive
Project Type: Custom Software Development
S/N | Risk | Active | Probability | Impact | Risk Response | Owner
1 | Involvement of the delivery team in other projects/work related engagements leading to delay in delivery | No | Low | Timeline delay | Reduce workload of key resources on the project so that they can have additional time | Wragby
[5 empty] | Deploy additional resources on the project and ensuring they can focus on the project and are not distracted by other projects | Wragby
2 | Wrong service domain split | No | Medium | Rework of service design, delays in development cycles | Conduct early domain-design workshops and validate service maps before coding | Qore
3 | Architectural design issues | No | Low | Performance issues, scalability constraints, need for redesign | Validate architectural approach with the Qore team before implimentation | Qore
4 | Undeclared dependencies | Undecided | High | Go-live failure or service malfunction | Ensure all dependencies are declared and provided | Qore
5 | Internal tool issues (e.g. nuggets) | Undecided | Medium | Performance degradation during test or production | Ensure tooling is updated, tested, and validated | Qore
6 | Legacy channel breakages (ATM, USSD, Agency) | Undecided | Medium | Customer downtime at go-live; failed transactions | Build compatibility layers and test thoroughly in sandbox environments | Qore
7 | Likely SME unavailability | No | Low | Slow resolution of blockers, delayed testing and UAT | Block SME time in calendar. Delegate other resources | Qore
8 | Mismatch of developed solution to requirments | No | Medium | Delay in development | Conduct periodic internal and external reviews with Qore team | Wragby, Qore

## Active
Project Type: Custom Software Development
S/N | Risk | Active | Probability | Impact | Risk Response | Owner
1 | Possible delay in delivering the solution due to the complexity of the solution | Yes | Medium | Timeline delay | Qore team to be available to provide walkthrough of the system when needed | Wragby
[5 empty] | Qore team to share detailed solution process flows, business rules and requirement documents | Wragby
Share any technical documentation with the development
provide complete information on the solution architecture
2 | Delays in providing authentication dependencies and requirements | Yes | Medium | Delay in overall project timeline | Continue development on non-dependent tasks | Wragby
[5 empty] | Expidite provision of authentication dependencies and requirements | Qore
3 | Third-party integration delays | Yes | High | Delay in dependent service readiness and end-to-end testing | share the list of the third party integrations | Qore
Establish early engagement with third-party vendors to understand dependencies and SLAs
Begin integration discussions early; follow up continuously
4 | Continuous updates on the environment by the Qore team | Yes |  | Possible code conflict | Qore team to put a process for pushing updates
Qore team to establish and communicate clear scope with regards to what is being pushed and how it affects the work being don by the dev team

## Sheet3
S/N | Risk | Active | Probability | Impact | Risk Response
1 |  | Yes | Medium | Timeline delay