## Sheet1
RISK REGISTER
Document Name | Risk Register – Xidoc ERP Implementation
Department | Digital Advisory
Customer Name | Codix Ghana
Stage Gate | Planning
Project Type | ERP Implementation
Risk ID | Risk Description | Risk Category | Likelihood | Impact | Risk Rating | Project Lifecycle Stage | Response Strategy | Risk Response Plan | Risk Owner | Status
R1 | The shared prototype appears incomplete. While the FRD captures the requested features, foundational/enabling features (e.g. product creation, inventory, GRN) may be missing — risking a system that meets stated requirements but is not fully functional or usable by the client. | Requirements / Scope | High | High | High | Requirements / Design | Mitigate | Review the prototype and FRD against a complete list of required ERP features. Have the design team update the prototype to include enabling features (product, inventory, GRN) and confirm completeness with stakeholders before development proceeds. | Tofunmi Akinbo (Design/BA) | Open
R2 | No agreed definition of the standard, non-negotiable ERP features that must exist beyond the prototype specifics, creating a risk of building the wrong scope or omitting essential functionality. | Requirements / Scope | Medium | High | High | Requirements / Design | Mitigate | Hold the scheduled alignment session for Temitope to walk through the list of standard features available in the Codix system. Document the agreed must-have features in the FRD before build. | Temitope Alabi / Tofunmi Akinbo | Open
R3 | Features not included in the original plan may be identified mid-timeline, requiring requirement changes and additions that expand scope and affect the delivery timeline. | Scope / Schedule | Medium | Medium | Medium | Planning / Development | Mitigate | Route new or changed requirements through the standard change-control process onto the backlog. Allow Daniel to prioritise urgent items and update the work breakdown and timeline whenever scope changes are accepted. | Halimat Abdul-Lateef (PM) / Daniel | Open
R4 | The assigned developer also supports other (currently stable) projects. Production issues on those projects would need to be attended to, diverting effort from the current sprint and delaying deliverables. | Resource / Staffing | Medium | Medium | Medium | Development | Mitigate | Keep communication lines open with the PM/management when other-project demands arise. Allow Daniel to prioritise and combine work where possible, and reflect any diversion in the timeline. | Lawrence Ehimhen / Daniel | Open
R5 | The assigned developer is working on the Codix project for the first time and needs time to ramp up on the codebase, unlike experienced team members, which may have a minor impact on the timeline. | Resource / Knowledge | Medium | Low | Low | Development | Mitigate | Allocate time for the developer to study the codebase, provide access to comparison/architecture documents, and make senior developers (Temitope/Lawrence) available for support. | Damilola Adeniyi / Lawrence Ehimhen | Open
R6 | The revamped Codix environment must be fully regression-tested to confirm existing functionality still works before it replaces the current staging build; incomplete testing could introduce regressions or delay dependent work. | Technical / Quality | Medium | Medium | Medium | Testing / Deployment | Mitigate | Complete end-to-end regression testing of the revamp. Apply simple fixes/updates as bugs are found and have developers pull the updates. Replace staging only after verification is complete. | Lawrence Ehimhen / Joy Ben (QA) | Open
R7 | There is no documentation covering the full current system, and some requirements were communicated verbally. This limits QA's ability to write test cases and validate the revamped environment. | Documentation / Quality | High | Medium | High | Requirements / Testing | Mitigate | Share existing product/functional documentation with QA. Generate additional process/code documentation over time (e.g. leveraging AI across the large codebase) and sync on what documentation is available on each side. | Halimat Abdul-Lateef / Lawrence Ehimhen | Open
R8 | Development must align with the revamp's new service/controller-based architecture and model structure; building on a different structure could cause rework and affect design decisions. | Technical / Architecture | Medium | Medium | Medium | Design / Development | Mitigate | Align the model structure with the revamp during the technical session and reuse existing services/controllers where possible. Have the developer pull the revamp branch before building. | Temitope Alabi / Damilola Adeniyi | Open
R9 | The solution is built on Codix Nigeria, but the client requires a Codix Ghana UI that is entirely different. Without a clear FRD of Ghana-specific items, the delivered solution may simply replicate Codix Nigeria rather than meet Ghana's needs. | Requirements / Design | Medium | Medium | Medium | Design | Mitigate | Produce an FRD/story listing the items that must appear on Codix Ghana and the required UI differences, and confirm with stakeholders before build. | Tofunmi Akinbo / Lawrence Ehimhen | Open
R10 | The new developer may not yet have access to the correct repository and revamp branch (WBiz Manager), which could delay the start of development. | Technical / Access Management | Low | Medium | Low | Setup / Development | Mitigate | Confirm and grant the developer access to the WBiz Manager repository and revamp branch before development begins. Developer to pull the code and raise any access issues early. | Temitope Alabi / Lawrence Ehimhen | Open
R11 | Illness or indisposition of a key developer could delay tasks. The work breakdown includes limited buffer, though a backup can step in for short absences. | Resource / Staffing | Low | Medium | Low | Development | Mitigate | Build buffer into the work breakdown, identify backup resources (senior developers) who can step in for short absences, and keep communication open on availability. | Lawrence Ehimhen / Halimat Abdul-Lateef | Open
R12 | It is unclear whether the build should follow general ERP domain standards or simply adapt Codix Nigeria. This needs confirmation with Daniel to avoid rework or delivering a non-standard solution. | Governance / Standards | Medium | Medium | Medium | Planning / Design | Mitigate | Halimat to consult Daniel on the applicable ERP standards and approach, and capture the agreed standards before or at the technical alignment session. | Halimat Abdul-Lateef / Daniel | Open
R13 | Delays in client sign-off on requirements, the prototype, or deliverables (a risk flagged at project inception) could delay project progression. | Project Management / Schedule | Medium | Medium | Medium | Planning / All Stages | Mitigate | Share the prototype, FRD and work breakdown with the client early for review, obtain formal sign-off at each gate, and track approvals against the timeline. | Halimat Abdul-Lateef (PM) | Open