## Risk Register v2
A4&T RISK REGISTER
Project Type: ERP Implementation
ID | PLC | Date (mm/dd/yyyy) | RISK | MATERIALIZED RISK? | PROBABILITY 1-5 | IMPACT 1-5 | PI SCORE | RISK RANKING | IMPLICATION | RISK RESPONSE/MITIGATION | RESPONSE OWNER | EXPECTED RESPONSE IMPACT | ACTUAL RESPONSE | ACTUAL RESPONSE IMPACT | PROBABILITY 1-5 KEY | IMPACT 1-5 KEY
RSK001 | ALL PLC |  | Unavailability of delivery team due to Involvement in other projects/work related engagements, sickness, leave, resignation, contract expiration etc. | Yes | 3 | 4 | 12 | High | All | Plan the development with disruptions in mind. | SE, PM | The project should not suffer from resource constraints
[10 empty] | Negotiate with functional manager for a replacement resource | SE
[10 empty] | Employ more resources | Wragby
Closure
[10 empty] | Review the requirements with the Wragby team before implementing | SE, PM
[10 empty] | Review development with the client before marking the module as done. | Development team (SE & PM)
[10 empty] | Build according to specification | SE
[10 empty] | Conduct proper test (Unit, regression) | SE
[10 empty] | Conduction proper internal user acceptance test before reviewing with the customer | Tester
[10 empty] | Utilize the Azure Board for storing requirements, and hold a session with all project team members to ensure there is a common understanding on how to use the board | Development team
RSK002 |  |  | Realistic timeline is greater than budgeted timeline as a result of improperly scoped requirements | Yes | 4 | 4 | 16 | Very High |  | Include additional resource (Consider schedule crashing to save cost if possible)
Consider moving low priority items to support phase
Raise change requests to reflect changes in timeline if the above mitigation are futile
RSK003 |  |  | Inaccurate estimated timelines provided during the schedule/sprint planning sessions | Yes | 3 | 4 | 12 | High |  | Involve technical resource in sprint planning session
When performing schedule/sprint planning, ensure the team does not have knowledge of the planned timeline to ensure estimated timeline is realistic
Involve another resource in the schedule/sprint planning to serve as a quality check
RSK004 | Planning |  | Inability of client to provide accurate requirements |  | 3 | 4 | 12 | High | All | Ask probing and critical questions | BA, SE | The team will uncover requirements that were not initially mentioned, thus helping the team to develop a solution that aligns with the customer's expectation
RSK005 | Planning |  | Unavailability of stakeholders for requirement gathering, validation and review |  | 2 | 3 | 6 | Medium | Schedule | Delegate another team member to handle the session and record the session | Customer | The project would run according to schedule
[10 empty] | Raise a change request to request for the project to be moved/extended (This may incur cost) | Customer
Prioritize involvement of assigned resources on the project
RSK006 | Execution |  | Possibility of not providing a significant increment by the end of the sprint |  | 2 | 4 | 8 | Medium | Schedule | Review validated requirements and commence development immediately | SE, BA | Usable increment is available as at schedule
[10 empty] | Resources need to prioritize portfolio and ensure that a usable increment is available as at when scheduled | SE
RSK007 | ALL PLC |  | Scope Creep. | Yes | 3 | 4 | 12 | High | All | Hold scope validation session with the internal team and stakeholders team to align on understand. | PM | Project runs according to scope
[10 empty] | Get customer sign off on requirements |  | 0
[10 empty] | Build to specification | SE
Raise change request if scope differs from original requirements
RSK008 | Execution |  | The deployment of relatively new/different resources on the project could lead to further delays in development as a result of the resources' unfamiliarity with the product | Yes | 3 | 4 | 12 | High | Schedule | Ensure proper hand-holding sessions are held with the deployed resources. | SE
[10 empty] | Developers familiar with the solution should ensure proper monitoring of the development work of the resources | SE
[10 empty] | Estimate progress periodically to ensure we can still meet up with timelines (Check progress on DevOps) | SE, PM
[10 empty] | Communicate any issues that could lead to delays proactively | SE
Raise change requests if resource change would unavoidably impact project constraints
RSK009 | Execution |  | Risk of delay due to the replacement resource's unfamiliarity with the frontend language | Yes | 3 | 4 | 12 | High | Schedule | Negotiate with functional manager for supporting or replacement resource familiar with the language
In the absence of replacement resource, factor training period and raise change request for extension of schedule
Negotiate with the departing resource to work part-time (by utilizing contigency reserve captured as risk during the costing)
Consider schedule crashing by utilizing both part-time and full-time resource
RSK010 |  | 2024-08-26 | Possibility of sprint 1 not completing as scheduled |  | 3 | 3 | 9 | Medium |  | Balance timeline by reducing timeline for other sprints
RSK011 | Closure |  | Lack of adoption of the solution by the customer |  | 5 | 4 | 20 | Very High | Quality | Conduct online training Conduct offline/physical training Create a whatsapp group for quick resolutions of issues and request Develop a robust change management plan | Project Manager | Full Adoption of the system
RSK012 | ALL |  | Delays in signing off | Yes | 4 | 3 | 12 | High | Schedule | Continuous communication with the customer | Project Manager | Quicker sign off
RSK013 | Execution |  | Delay in developing Project Module | Yes | 5 | 4 | 20 | Very High | Schedule | Division of project into two phases Leverage internal resources for swift development Deliver completed modules to the customer to commence usage | Project Manager
RSK014 |  |  | Extension of project timeline | Yes | 5 | 4 | 20 | Very High | Schedule | Bundle the development of the project module with other customers' apart from A4&T's request Bill the cost of development to Wragby | Wragby

## Issues Log (hidden)
ID | PLC | Risk ID | Module | Issue | Owner | Priority | Status | Date (dd/mm/yyyy) | Resolution Date
IS001 |  | RSK001 |  | Unavailability of delivery team due to Involvement in other projects/work related engagements, sickness, leave, resignation, contract expiration etc. | Emmanuel
IS002 |  |  |  | Realistic timeline is greater than budgeted timeline as a result of improperly scoped requirements
IS003 |  | RSK003 |  | Inaccurate estimated timelines provided during the schedule/sprint planning sessions
IS004 |  | RSK007 |  | Scope Creep
IS005 |  | RSK008 |  | The deployment of relatively new/different resources on the project could lead to further delays in development as a result of the resources' unfamiliarity with the product
IS006 |  | RSK009 |  | Risk of delay due to the replacement resource's unfamiliarity with the frontend language
IS007 |  | RSK012 |  | Delays in signing off
IS008 |  | RSK001 |  | Unavailability of delivery team due to Involvement in other projects/work related engagements, sickness, leave, resignation, contract expiration etc. |  |  | In Progress | 2024-10-04
Absence of front-end engineer (Mancha) for two weeks on the project led to delays
Delays in completing feature by backend developer, leading to delays in the work the Front-end engineer had to do
IS009 |  |  | Invoice | The save button functions as the send button, leaving no room for reviewing | Mark | Medium | Active
IS010 |  |  | Sales | Ability to edit payment schedule before they start paying | Mark |  | Active
IS011 |  |  |  | Inability of sales, account or customer service to view ongoing part payment details e.g amount paid, balance etc | Mark & Emmanuel |  | Resolved
Delay in completion of features due to additional complexities
IS012 |  |  | General | User role error |  |  | Active
|  |  | HR | Error in activating performance year |  |  | Active
|  |  | HR | failure message on sending performance appraisal for approval |  |  | Active
|  |  | HR | Error on clicking on Finish for appraisal by Supervisor |  |  | Active
|  |  | HR | Relax delegated employee for the leave aspect for departments that have only one staff. |  |  | Active
|  |  | HR | Leave Approval should be: Initiator – Line Manager. HR can view, It should only go to MD if the person is directly reporting to the MD |  |  | Active
|  |  | Journal | Journal list needs to be searchable | Emmanuel |  | Resolved
|  |  | Payroll | failure message when MD try to approve payroll |  |  | Active
|  |  |  | There is no send to BM for approval button for quote in operations | Mark |  | Active
|  |  |  | Fix breadcrumb navigation issue on sales quote for operation |  |  | Active
|  |  |  | Inability to filter by product and search inventory report |  |  | Active
|  |  |  | Ability to view payslip once approved by MD |  |  | Active
|  |  |  | Remove the ability to delete approved invoice |  |  | Active
|  |  |  | Fix error with deleting asset category | Mark |  | Active
|  |  |  | Possible delay in timeline due to unavailability of resource - laptop | Damilola | Low
Possibility of rework on engineering and operations module due to conflicting requirement
Possible delay with Multi entity
Use of save button has send button
Edit part of the payment schedule is not done
Inability of sales, account or customer service to view ongoing part payment