## Risk Register
Project Type: Cloud Migration
S/N | Risk | Probability | Impact (1-5) | Rating |  | Risk Response | Owner
1 | Involvement of the delivery team in other projects/work related engagements leading to delay in delivery | 70% | 3 |  | i | Reduce workload of key resources on the project so that they can have additional time
[5 empty] | ii | Deploy additional resources on the project and ensuring they can focus on the project and are not distracted by other projects
2 | Delays on the revieving the quest tool | 100% | 5 |  | i | Escalate to Wragby contact at quest
[5 empty] | ii | Pacify customer during wait period
[5 empty] | iii | Conduct all pre-migration activities in the meantime
3 | Go daddy can be tricky and petty when customer's migrate off their tenant |  |  |  |  | Do not inform Go Daddy of inpending migration
Wragby resource is knowledgable enough with go daddy to overcome the hurdle
4 | Customer adding more users to be migrated |  |  |  | i | This should be accounted for when purchasing any tools
| Uncerainty on email back-up tool |  |  |  | i | Hold sesions with the tool providers and examin our options
[5 empty] | ii | Customer to ahead with purchasing Baracuda tool

## Issue Log
ID | PLC | Issue | Status | Delay in Days | Owner
IS001 | Execution | Involvement of the delivery team in other projects/work related engagements | Active |  | Customer
IS002 | Execution | Unavailability of Project Resource from WRAGBY | Active |  | Wragby
IS003 | Execution | Possibility of not providing a significant increment by the end of the sprints | Active |  | Wragby
IS004 | Execution | Change in tool being used for email back up | In Progress |  | Customer
IS005 | Execution | Delay in receiving migration tool | Completed |  | Wragby