## Risk Register
Risk Register
Project Type: Cybersecurity Implementation
ID | Description of Risk | Impact | Risk Reponse | Risk Level | Risk owner | Notes | Severity 1-5
1 | Unavailability of Key Project Stakeholders/Resources | Project delay | Project team to make provision for unavailable resources with replacements and timely communication | High | Afromedia |  | 5
2 | Scope Creep | Project delay, project quality | A Change Control process is in place to handle this | Medium | Afromedia/Wragby |  | 3
3 | Delay in provision of requirements | Project delay |  |  | Afromedia |  | 5
4 |  | Project delay | Would go through a Change Request control process | High | Afromedia/Wragby |  | 2
5 | Project Documentation | Project delay | Shared documentations on project | Medium | Afromedia |  | 2