## Risk Register
Risk Register
Project Type: Proof of Concept (PoC)
ID | Description of Risk | Probability | Impact | Risk Score | Implication | Risk Reponse | Risk Level | Risk owner | Notes
1 | Unavailability of Key Project Stakeholders/Resources | 5 | 5 | 25 | Project Timeline | Project team to make provision for unavailable resources with replacements and timely communication | High | ARM
2 | Scope Creep | 4 | 4 | 16 | Project Scope, project quality | A Change Control process is in place to handle this | Medium | ARM/Wragby
3 | Internet Connection | 4 | 4 | 16 | Project Timeline | Increase Bandwidth | Medium | ARM
4 | Complexity around Security | 3 | 5 | 15 | Security | Azure spends so much on security for safeguarding client data from cyber threats. The following configuration are required •Allow multi-factor authentication •Encrypt data assets in migration and at rest •Establish user access policies •Train others on the ways of maintaining security in the cloud •Execute required controls •Set individual workloads apart for reducing every damage that could happen because of an attacker | High | ARM/Wragby
5 | Platform and Database Credentials Sharing | 5 | 3 | 15 | Information Security | Credentials to be shared via a secure link to be created to one person at a time | High | ARM/Wragby
6 | Communication among project Stakeholders | 5 | 3 | 15 | Information Security | Communication to be controlled by establishing a single point of contact who manages and controls information flow via emails | High | ARM/Wragby
7 | Denial of Service | 3 | 5 | 15 | Information Security | Implement DDOS controls on Azure to mitigate these attacks by ensuring use of Private IPs across all users | High | Wragby