## Sheet1
Project Type: ERP Implementation (Microsoft Dynamics 365 BC)
Risk Description | Probability (H/M/L) | Impact (H/M/L) | Impact On | Owner | Mitigation Steps
Delay in provision of all requirements on project | H | H | Schedule | TNL | Schedule will be rebaselined pending feedback on when these requirements will be provided. A cost and Material mode of payment will be activated to calculate for days lost
Scope creep | L | L | Schedule | TNL/Wragby | A change management process will be activated
Unavailability of Key Project Stakeholders/Resources | H | H | Schedule | TNL/Wragby | The responsible parties will assign key resources to mitigate the risk
Unavailabilty of the required API for integration where applicable | M | M | Scope & Schedule | TNL | Provide required APIs from third party
Delay in Project documentation execution, Documents such as SOW, Project Charter, FRD | H | H | Scope & Schedule | TNL | Project will be on hold until documents are signed off and the build phase can commence